## Slide 1: Housekeeping Lean Process
Initial Team Focus:
  Procedure for Definition and Release of a new housekeeping charge
  Procedure to Determine Staffing Levels of a charge
  Procedure for Revising and Updating the contents of a charge
  Procedure for Housekeeper Quality Checklist of charges in a building
  Procedure for Customer Complaints
  Procedure for Housekeeping Corrective and Preventative Actions
  Development of Customer Satisfaction Metrics and Key Housekeeping Quality Indicators
  Create Process Documentation Model and Record Archive Procedure
Notes: Committed to …Inch Wide Mile Deep

## Slide 2: Housekeeping Lean Process
Current Status
    Mapping As-Is Process
    Created Problem Parking Lot
      No clear understanding of who owns the charge- Housekeeping or Customer
      Level of Detail not consistent within the charge or across charges
      Housekeeper has very little input on the process of developing charge
      Housekeepers filling-in on a charge do not have proper training to do the charge effectively

## Slide 3: Housekeeping Lean Process
Metrics Sub Team
    James Allen
    Ed Andrews
    Thomas Buddy
    Gwen Glattes
    Lorenzo Jackson
    Tayo Kuku
    Ross Leiman
    Betsy Robinson
Voice of the Customer
Thomas Buddy
Brian Devers
Seth Fitzgerald
Tayo Kuku
Dave Parker
Betsy Robinson
Robert Whitehouse

## Slide 4
Chart: Full Lean Process Roll Out Timeline
| Lean Process Training | Procedure for definition and release of a new housekeeping charge | Procedure for determining staffing levels of charges | Procedure for revising & updating the contents of a charge | Procedure for housekeeper quality checklist of charges in a building | Process documentation model and record archive procedure | Customer complaint procedure | Housekeeping corrective and preventive action procedure | Procedure for Customer satisfaction metrics and key housekeeping quality indicators
Start Display | 41688 | 41699 | 41699 | 41699 | 41699 | 41760 | 41791 | 41730 | 41821
Offset | 2 | 80 | 90 | 60 | 90 | 61 | 152 | 213 | 122